## Project charter
Project charter
Project name: | Implementing Dropbox
Sponsor: | John Peterson - Director, Innovation
Manager: | Jiri Benedikt - Lean manager
Project team: | Name | % FTE
| Denise Adams (IT) | 10%
| Roy Biggs (HR) | 20%
| Rose Bronson (Innovation team) | 20%
Project description | The number of employees and the volume of shared data in recent years has grown so much that the team loses a lot of time searching for information. There is no archivation process or process for handing data after someone leaves. Dropbox was chosen as a vendor for cloud data storage for the team.
Project goals | Create a place to store documents, set up structure for storing data, design processes and standard operationg procedures and train all employees. Then migrate the data from old structure to new structure. The goal is to minimize searching and data loss.
Measurable benefit | KPI | Current | Goal
| % Of company data stored at Dropbox | 0% | 100%
| % Of employees using Dropbox | 0% | 100%
| % Tems with Dropbox implemented | 0% | 100%
Scope | In scope | Out of scope
| Dropbox system: Technical setup Documents tructure, Processes, Standards Migration Training | Accounting data Data warehouse / Reporting data Physical documentation and related processes Document workflows
Milestone | Milestona name | Date
| Kickoff | 2020-03-02
| Milestone 1: Pilot with first 3 teams finished | 2020-04-26
| Milestone 2: Rollout to all teams | 2020-06-21
| Project closeout | 2020-06-21
Risks | Risk | How to mitigate the risk
| Employee resistance against drombox | Include people in designing the structure, train dilligently, implement division champions, get feedback often
| Technology limits of Drobox will make implementing intedned processes iposible | Check everything with trial version, share experience with Dropbox
| The usage will drop after some time | Have a review meetings every 6 months
| Hacker attack, data loss or theft | Educate on IT security during dropbox trainings, external IT company will check antivirus software
Requirements | Requirement description | To who | Expected cost / time
Internal + External | Physical migration of data to new folders | Interns | tens of hours
| Physical instalation to individual computers | Interns | tens of hours
Communitation plan | Item | Responsible | Frequency
| Project status meeting | Jiří Benedikt | Weekly
| Steering Committee | Jiří Benedikt | Every 4 weeks
| Project Newsletter | Jiří Benedikt | Every month

## Project Plan (after Milestone1)
| Milestone 1 | [8 empty] | Milestone 2
Project week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | End of milestone 1 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | End of milestone 2
| 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-26 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-21
Team availability
Team member 1
Team member 2
Team member 3
Team member 4
Team member 5
Team member 6
Team member 7
Topic | Activities | Activities | Activities | Activities | Activities | Activities | Activities | Activities | Outomes and Deliverables | Activities | Activities | Activities | Activities | Activities | Activities | Activities | Activities | Outomes and Deliverables
Communication and training | 2020-03-02: All employees communication. Choosing champions for each eam; 2020-03-09: Mini training (1h) of team champions on Dropbox; 2020-03-23: Status update email to all employees; 2020-04-20: Status update to all employees; 2020-04-26: Everyone knows the benefits of moving to dropbox, team champions trained; 2020-06-21: Everyone trained, feedback being collected
Technical installation | 2020-03-02: Set up a trial version of Dropbox Business; 2020-03-09: Test all the functionalities needed; 2020-04-26: Dropbox set up and works in the free trial version; 2020-06-21: Dropbox business licenced for all employees
Data strucutre and processes | 2020-03-09: Design a company wirde project strucutre; 2020-03-16: Team champions will design their teams data strucutre with their teams; 2020-03-23: Division champions hand in finished data strucutre; 2020-04-26: Processes and standards on how to structure and work with data are finalized.; 2020-06-21: Processes ě standards are documented, owners and update process exist
Implementation in Logistics team | 2020-03-09: Design data strucutre; 2020-03-16: Data migration; 2020-03-23: Check, instalation; 2020-03-30: Training+ Go-Live Logistics; 2020-04-26: Dropbox implemented in team Logistics; 2020-06-21: Dropbox implemented with ongoing fine-tuning and Q&A
Implementing in Office management + Finance team | 2020-03-16: Design data strucutre; 2020-03-23: Data migration; 2020-03-30: Check, instalation; 2020-04-06: Training+ Go-Live Office management + finance; 2020-04-26: Dropbox implemented in Office management + finance team; 2020-06-21: Dropbox implemented with ongoing fine-tuning and Q&A
Implementing in head office team | 2020-03-23: Design data strucutre; 2020-03-30: Data migration; 2020-04-06: Check, instalation; 2020-04-13: Training+ Go-Live Head office; 2020-04-26: Dropbox implemented in Head office; 2020-06-21: Dropbox implemented with ongoing fine-tuning and Q&A
Implementation in sales teams | 2020-03-23: Sales teams leaders suggest in which week they will migrate; 2020-04-20: Migration plan for sales offices finalized; 2020-04-26: Sales teams know how and when they will be migrated to Dropbox; 2020-06-21: Dropbox implemented with ongoing fine-tuning and Q&A

## Action&Decision Log
Action and decision log
Decision | Date
Task | Owner | Deadline | New Deadline | Notes | Status

## Weekly status update - Week 5
Weekly status update
Project: | Implementing Dropbox | 0 | Project status: | Some deliverables late
Project week no | 5 |  | Milestone deadline | 2020-04-26
Week starting: | 2020-03-30 |  | Project end | 2020-06-21
Dostupnost členů týmu
Člen 1
Člen 2
Člen 3
Člen 4
Člen 5
Člen 6
Člen 7
Topic | Last week's planned activities | Remarks | Following week's planned activities | Outomes and Deliverables
Communication and training |  |  |  | Everyone knows the benefits of moving to dropbox, team champions trained
Technical installation |  |  |  | Dropbox set up and works in the free trial version
Data strucutre and processes |  |  |  | Processes and standards on how to structure and work with data are finalized.
Implementation in Logistics team | Training+ Go-Live Logistics | Will not be finished by the end of the milestone. The reason is sudden resignation of Logistics manager. Will be postponed to the next milestone. |  | Dropbox implemented in team Logistics
Implementing in Office management + Finance team | Check, instalation | We have 1 week delay as we were bocked by the logitics situation. The milestone outcome is not endangered. | Školení + Go Live - Office management + Finance | Dropbox implemented in Office management + finance team
Implementing in head office team | Data migration | We have 1 week delay as we were bocked by the logitics situation. The milestone outcome is not endangered. | Kontrola, instalace | Dropbox implemented in Head office
Implementation in sales teams |  |  |  | Sales teams know how and when they will be migrated to Dropbox

## Quick Manual
Before the project start
Fill in the project charter and have it approved
Project plan:
Split your project into an 8-week milestones / project phases (rows)
Split the projects into 3-10 categories of activities (rows) - such as communication, technical, analysis, etc.
For each category, fill in the deliverables for each milestone
Before the start of every milestone (project phase)
Plan activities for every week of the milestone to get the deliverables done
Do not change the plan during the milestone!
Run a kick-off meeting
At a first weekly project meeting
Check what needs to be done, split task in Action&Decision log
At each following meeting
Check tasks due in past week and mark if they were done or not
Check pask weeks activities from the project plan and color them:
Green | Finished
Yellow | Not done, but the milestone deliverable is still doable
Red | Not done and we already know that the milestone deliverable will not be met
If some yellow activities from previous weeks are done, you can make them green
Split tasks for next week
Send a Weekly status update to the sponsor / steering committee
At the end of the milestone
Check the project plan, present results to the sponsor / steering comittee
If necessary, replan the deliverables for next milestones
Repeat